## LPDDR3_pre-DVT_AA Version
CaseID | Test Case | Actual | Progress | Status | Result | Remark | Bug num
15001 | TT DDR-Power supply(RT)(DL/Boot Up,APK light load) |  | 100% | Ongoing | Pass
15001001 | VDDCORE |  | 100% | Closed | Pass
15001002 | VDD1 |  | 100% | Closed | Pass
15001003 | VDD2 |  | 100% | Closed | Pass
15001004 | VDDCA |  | 100% | Closed | Pass | 与VDD2是同一个电源域
15001005 | VDDDQ |  | 100% | Closed | Pass | 与VDD2是同一个电源域
15001006 | VrefCA |  | 100% | Closed | Pass
15001007 | VrefDQ |  | 100% | Closed | Pass | VrefCA和VrefDQ共用一个电源域
15002 | TT DDR-Power supply(RT)(APK henvy load ,APK Monkey) |  | 100% | Closed | Pass
15002001 | VDDCORE |  | 100% | Closed | Pass | ripple min值和max值超过了4%，VDDCORE改为双面贴片电容方式测试pass | 831514
15002002 | VDD1 |  | 100% | Closed | Pass
15002003 | VDD2 |  | 100% | Closed | Pass
15002004 | VDDCA |  | 100% | Closed | Pass | 与VDD2是同一个电源域
15002005 | VDDDQ |  | 100% | Closed | Pass | 与VDD2是同一个电源域
15002006 | VrefCA |  | 100% | Closed | Pass | VREF满足spec，比较margin，后续稳定性测试继续跟踪
15002007 | VrefDQ |  | 100% | Closed | Pass | VrefCA和VrefDQ共用一个电源域
15003 | TT DDR-Initialization(RT)(DL /Boot Up) |  | 100% | Closed | Fail
15003001 | tINIT 0 |  | 100% | Closed | Fail | tINIT 0 test value is 284 ms, spc defined value is smaller than 20 ms. | 819460
15003002 | tINIT 1 |  | 100% | Closed | Pass
15003003 | tINIT 2 |  | 100% | Closed | Pass
15003004 | tINIT 3 |  | 100% | Closed | Pass
15003005 | tINIT 4 |  | 100% | Closed | Pass
15003006 | tINIT 5 |  | 100% | Closed | Pass
15003007 | tZQINIT |  | 100% | Closed | Pass
15004 | TT DDR-DDR scan(RT/HT/LT) |  | 100% | Closed | Pass
15004001 | DDR scan RT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004002 | DDR scan LT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004003 | DDR scan HT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004004 | Binary Check(1cs/2 cs) |  | 100% | Closed | Pass
15005 | TT DDR-Signal Intergity(RT)(DL/Boot Up,APK light load) |  | 100% | Closed | Pass
15005001 | Signal when power up |  | 100% | Closed | Pass
15005002 | CLK signal |  | 100% | Closed | Pass
15005003 | CA signal |  | 100% | Closed | Pass
15005004 | CA timing |  | 100% | Closed | Pass
15005005 | CKE signal |  | 100% | Closed | Pass
15005006 | CKE timing |  | 100% | Closed | Pass
15005007 | DQS signal-write |  | 100% | Closed | Pass
15005008 | DQS timing-write |  | 100% | Closed | Pass
15005009 | DQ signal-write |  | 100% | Closed | Pass
15005010 | DQ timing-write |  | 100% | Closed | Pass
15005011 | DQS signal-read |  | 100% | Closed | Pass | only as reference
15005012 | DQS timing-read |  | 100% | Closed | Pass
15005013 | DQ signal-read |  | 100% | Closed | Pass | only as reference
15005014 | DQ timing-read |  | 100% | Closed | Pass
15005015 | CS signal |  | 100% | Closed | Pass
15005016 | CS timing |  | 100% | Closed | Pass
15006 | TT DDR-Signal Intergity(RT)(APK henvy load ,APK Monkey) |  | 99% | Closed | Pass
15006001 | Signal when power up |  | 100% | Closed | Pass
15006002 | CLK signal |  | 100% | Ongoing | Pass
15006003 | CA signal |  | 100% | Closed | Pass
15006004 | CA timing |  | 100% | Closed | Pass
15006005 | CKE signal |  | 100% | Closed | Pass
15006006 | CKE timing |  | 100% | Closed | Pass
15006007 | DQS signal-write |  | 100% | Closed | Pass | tDS fail，去嵌之后pass | 819503
15006008 | DQS timing-write |  | 100% | Closed | Pass
15006009 | DQ signal-write |  | 100% | Closed | Pass
15006010 | DQ timing-write |  | 100% | Closed | Pass
15006011 | DQS signal-read |  | 100% | Closed | Pass | only for reference information
15006012 | DQS timing-read |  | 100% | Closed | Pass | only for reference information
15006013 | DQ signal-read |  | 100% | Closed | Pass | only for reference information
15006014 | DQ timing-read |  | 100% | Closed | Pass | only for reference information
15006015 | CS signal |  | 100% | Closed | Pass
15006016 | CS timing |  | 100% | Closed | Pass
15007 | TT DDR-Core AC timing(RT) |  | 100% | Closed | Pass
15007001 | TT DDR-Core AC timing(RT) |  | 100% | Closed | Pass | AC_timing:tRFCpb=11.8ns,spec上面规定是大于或等于90ns 逻分的自动测试软件有一些问题，没有更新到最新版，现在无法测量这个参数 | 819445
15009 | TT DDR-Function Check(Kinds of Training,MR4...) |  | 100% | Closed | Pass
15009001 | Function Check(Kinds of Training,MR4...) |  | 100% | Closed | Pass
15011 | TT DDR-self-refresh AC timing(RT)_LPDDR3 |  | 100% | Closed | Pass
15011001 | TT DDR-self-refresh AC timing(RT)_LPDDR3 |  | 100% | Closed | Pass
15017 | TT DDR-DFS timing(RT) |  | 100% | Closed | Pass
15017001 | F0 to F1 |  | 100% | Closed | Pass
15017002 | F1 to F2 |  | 100% | Closed | Pass
15017003 | F2 to F0 |  | 100% | Closed | Pass
15017004 | SSC(EMI) |  | 100% | Closed | Pass
15017005 | Small scale DFS(EMI) |  | n/a |  |  | 此项不需要验证

## AC_timing_AA Version
933M_AC_timing
tREFW这个参数手动测试pass,自动测试LA的问题
逻分的自动测试软件有一些问题，没有更新到最新版，现在无法测量这个参数

## Function_Verify_AA Version
No. | No. | Issue&Warning Name | Property | Owner | Team | Status | Bug Num. | Remark | Risk&Issues debug status
1 | PWR&CLK&RST | Power |  |  |  | Done |  | 1.Power on: fail; | 1.Power on: tINIT0 fail;
[8 empty] | 2.Power off: pass; 3.Reboot: | 2.Power off: pass; 4.Reboot:
[8 empty] | 4.Low power: SW block; | 4.Low PWR: SW block;
|  | CLK |  |  |  | Done |  | 1.bringup:
2.Pre-DVT1: 3.Pre-DVT2:
4.SSC:
|  | RST |  |  |  | Done
2 | DDR INIT_releated | RL&WL check for DFS all frequency points |  |  |  | Done |  | 1.INIT flow check: MRW2 is OK, Pass;
2.DFS flow check: normal, Pass;
|  | ZQC flow check |  |  |  | Done |  | ZQC DDR side:
1.AC timing: done;
2.Waveform: Need to check with scope;
ZQC BB side: done, Pass
|  | MR4&MR8 |  |  |  | Done |  | MR4:done | 需要软件支持：开通MR4验证pass
|  | DDR INIT flow check |  |  |  | Done |  | OK
3 | Training_Related | Write leveling |  |  |  | n/a |  | PHY不支持write leveling | risk:如何控制skew？尤其高频对timing要求critial的情况？
|  | CA training check |  |  |  | Done |  | Standard mode: OK | 参考LP4X debug过程
byte mode: n/a
|  | DQ training check |  |  |  | Ongoing |  | DQ read training: OK | DDR scan check OK
[8 empty] | DQ write training: OK | DDR scan check OK
|  | Master BIST vs PHY BIST |  |  |  | Ongoing |  | HW training pattern: done | 提建议：后续项目支持可编程pattern
[8 empty] | SW DDR scan BIST pattern: | 发现LSFR DQ pattern并不random, 与designer沟通后验证OK;
Per-bit function check
|  | Multi-RANK training |  |  |  | Ongoing |  | OK
4 | New feature check | IP new feature check |  |  |  | n/a |  | edge mode: SS corner造沿有风险 | 待AB版本验证wide window mode
5 | DFS | DFS check |  |  |  | Done |  | 1.DFS flow and signal quality check:
[8 empty] | 2.Latency check: issues debug support: 双CA场景assert | 双CA场景频点为622MHz，latency消耗比较大的一点为SOC smart light，SW work around sloution: 双CA场景关闭smart light
3.Small scale DFS:n/a
4.AC timing:
5.SSC: pass
7 | Typical parameters check | tDQSS check |  |  |  | Done |  | It is OK; | It is OK;
|  | tDQSCK check |  |  |  | Done |  | It is OK; | It is OK;
|  | tDQS2DQ check |  |  |  | Ongoing |  | n/a
8 | I/O feature | I/V curve |  |  |  | Done |  | 需要软件支持提供minicode:done | 需要软件支持提供minicode:验证pass
9 | DDR SCAN | DDR scan log analysis |  |  |  | Done |  | 1.read DDRSCAN:Done | 1.read 眼图蘑菇状，需要配合diffential mode观察
2.write DDRSCAN:Done
3.CA DDRSCAN:Done

## Bug_Status_AA Version
SI/PI_related
No. | Issue&Warning Name | Property | Owner | Team | Status | Bug Num. | Remark | Debug status
1 | DDR tDH test fail@933MHz |  | Mark.Jiang |  | Closed | 819503 | interposer impact,信号经过de-embeded(interposer)处理后测试结果pass
2 | change topic: ddr scan test fail(SF/SS corner chip) |  | Longhua.Mai |  | Closed | 832077 | 重启问题解决，相关的DDR初始化变量没有得到初始化
3 | 233M/311M频点 DFS时会死机 |  | Yuelin.Tang |  | Need_Info | 833577 | eco回来后再进行debug
4 | POWER_off:异常和正常下电，VREF下电非常缓慢，在下电几毫秒之后VREF的电高于VDD1和VDD2，JEDEC上规定：VREF must always be less than all other supply voltages |  | Wayne.Liang |  | Closed | 821698 | 软件设置VREF先下电
5 | POWER:VDD_CORE的Vmax 934.5mV,Vmin 861.7mV都超过了spec；VREF的Vmin 584.9mV满足spec，后续稳定性测试继续跟踪； |  | Ping.Wei |  | Closed | 831514 | VDDCORE电容位置放置问题，VDDCORE将正面电容贴到反面
6 | Initialization Sequence:tINIT0大约284ms，JEDEC上面规定不超过20ms，而且刚起来的时候VREF的值是120mV，持续有270ms才上升到600mV |  | Kevin.Xie |  | Assigned | 819460 | SharkL3的这个问题，Robert.liu应该会有MF方案
7
8
9
10
AC Timing_related
No. | Issue&Warning Name | Property | Owner | Team | Status | Bug Num. | Remark | Debug status
6 | AC_timing:tRFCpb=11.8ns,spec上面规定是大于或等于90ns |  | Kevin.Xie |  | Closed | 819445 | 逻分的自动测试软件有一些问题，没有更新到最新版，现在无法测量这个参数
2
稳定性测试状态
No. | Issue&Warning Name | Property | Owner | Team | Status | Bug Num. | Remark | Debug status
1 | 压力测试reboot高温，出现1台3FF#0055定屏于spreadtrum界面，adb不可连 |  | Jingchao.Ye |  | Duplicated | 898290 | 手机已经切换到AB版，在AB版继续跟踪
2 | 压力测试reboot高温，出现3台3FF0029 3FF0130 3FF0055手机systemdump |  | lvqiang.Huang |  | Need_Info | 909219 | 手机已经切换到AB版，在AB版继续跟踪

## Risk_recording_AA Version
LPDDR3 New
| risk recording | Note
1 | AA version BB Vref比较margin，后续稳定性测试继续跟踪
2 | AA version BB tINIT 0 test value is 284 ms, spc defined value is smaller than 20 ms.
3 | 3FF rephone 高温环境reboot、高温环境monkey测试fail
4
5
6

## 稳定性验证_AA Version
Sharkl3_1 稳定性测试
TT DDR-Pressure Test(RT/HT/LT) | Test temperature | Test Time | Test PAC# | Test Status | Notes | Remark | Solution | BUG
DC Drop cycle | HT（65度） | 24H | W18.26.5 | pass |  |  | 手机SD卡没有log无法判断断电过程是否有问题
| LT（-20度） | 24H | W18.28.5 | pass
Sleep/Wake up | HT（65度） | 24H | W18.26.5 | pass
| LT（-20度） | 24H | W18.26.5 | pass
memtest+MP4 | HT（65度） | 24H | W18.26.5 | Pass
| LT（-20度） | 24H | W18.26.5 | Pass
Reboot | HT（65度） | 24H | W18.26.5 | Fail | 2FF#0215 reboot apk 只运行一次，手机不再反复重启；3FF#0055定屏于spreadtrum界面;2FF#0236、3SS#0323不反复重启；3FF#0029掉电 | W18.29.5 corner手机复测，3FF0029 3FF0130 3FF0055定屏，adb不可连 |  | Bug 909219
| LT（-20度） | 24H | W18.26.5 | Pass
Monkey | HT（65度） | 24H | W18.28.5 | Fail | W18.29.5 TT#0173复测pass | 3FF#0055 monkey停止，手机正常 |  | Bug 906716
| LT（-20度） | 24H | W18.28.5 | pass

## LPDDR3_pre-DVT_AB Version
CaseID | Test Case | Actual | Progress | Status | Result | Remark | Bug num
15003 | TT DDR-Initialization(RT)(DL /Boot Up) |  | 100% | Closed | Pass
15003001 | tINIT 0 |  | 100% | Closed | Pass | AB版修正AA版tINIT 0这个参数的问题
15004 | TT DDR-DDR scan(RT/HT/LT) |  | 100% | Closed | Pass | 两台TT refphone验证RT/HT/LT
15004001 | DDR scan RT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004002 | DDR scan LT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004003 | DDR scan HT(1cs/2 cs) |  | 100% | Closed | Pass | 1.pass or fail follow binary check结果；
15004004 | Binary Check(1cs/2 cs) |  | 100% | Closed | Pass
15006 | TT DDR-Signal Intergity(RT)(APK henvy load ,APK Monkey) |  | 100% | Closed | Pass
15006001 | Signal when power up |  | n/a
15006002 | CLK signal |  | 100% | Closed | Pass
15006003 | CA signal |  | n/a
15006004 | CA timing |  | n/a
15006005 | CKE signal |  | n/a
15006006 | CKE timing |  | n/a
15006007 | DQS signal-write |  | 100% | Closed | Pass | tDS fail，和AB版相似去嵌之后pass
15006008 | DQS timing-write |  | 100% | Closed | Pass
15006009 | DQ signal-write |  | 100% | Closed | Pass
15006010 | DQ timing-write |  | 100% | Closed | Pass
15006011 | DQS signal-read |  | 100% | Closed | Pass | only for reference information
15006012 | DQS timing-read |  | 100% | Closed | Pass | only for reference information
15006013 | DQ signal-read |  | 100% | Closed | Pass | only for reference information
15006014 | DQ timing-read |  | 100% | Closed | Pass | only for reference information
15006015 | CS signal |  | n/a
15006016 | CS timing |  | n/a

## 稳定性验证_AB Version
Sharkl3_1 稳定性测试
TT DDR-Pressure Test(RT/HT/LT) | Test temperature | Test Time | Test PAC# | Test Status | Notes | Remark | Solution | BUG
DC Drop cycle | HT（65度） | 24H
| LT（-20度） | 24H
Sleep/Wake up | HT（65度） | 24H
| LT（-20度） | 24H
memtest+MP4 | HT（65度） | 24H
| LT（-20度） | 24H | W18.32.6 | Fail | 1.3ss#1148视频播放出错; 2.3ss#0191视频播放退出了，apk停止了，然后出现systemdump |  |  | Bug918727 Bug918732
Reboot | HT（65度） | 24H
| LT（-20度） | 24H